## WBS Helpdesk System
CIHEUL TECHNOLOGIES - TAKE HOME PROGRAMMING TEST
Work Breakdown Structure (WBS) - Omnichannel Helpdesk & Real-time Support System
Arsitektur: Monorepo ¦ Backend: Python FastAPI ¦ Frontend: Vanilla JS Widget & Tailwind Web Dashboard ¦ Mobile: Flutter
WBS ID | Modul / Komponen | Fitur / Work Package | Rincian Task & Deliverables Teknis | User Role | Tech Stack | Durasi (Hari) | Bobot (%) | Prioritas | Kriteria Verifikasi (Definition of Done)
1.0 | Analisis & Desain | Spesifikasi & Blueprint Sistem | Analisis kebutuhan teknis dan proses bisnis helpdesk omnichannel | Semua Role | Markdown, Draw.io | 2 | 8 | Critical | Dokumen spesifikasi terverifikasi
1.1 | Analisis & Desain | BPMN Swimlane Diagram | Pemodelan proses bisnis 4 swimlanes (Customer, AI Bot, CS Agent, Supervisor) | Lead Architect | Draw.io / XML | 1 | 4 | Critical | File .drawio dan export PDF bersih
1.2 | Analisis & Desain | WBS & System Design | Penyusunan rincian WBS modular dan dokumen arsitektur database (ERD) & API contract | Tech Lead | Excel / Markdown | 1 | 4 | Critical | File .xlsx terformat rapi dan Architecture.md
2.0 | Backend Service | Core API & Database Engine | Fondasi RESTful API, database schema, otentikasi JWT dan manajemen tiket | CS, Admin | Python FastAPI | 3 | 15 | Critical | Backend running, API docs /docs aktif
2.1 | Backend Service | Database Schema & ORM | Modeling tabel Users, Customers, Tickets, Messages, KnowledgeBase dengan relasi ForeignKey | Backend Eng | SQLite / SQLAlchemy | 1 | 5 | Critical | Migrasi schema sukses, relasi cascade teruji
2.2 | Backend Service | Auth & RBAC Service | Autentikasi agen CS dan Admin berbasis JWT Token, password hash bcrypt | Admin, CS Agent | FastAPI Security, JWT | 1 | 5 | High | Endpoint login, refresh token, validasi role
2.3 | Backend Service | Ticket Management CRUD | API pembuatan tiket baru, update status (OPEN, IN_PROGRESS, RESOLVED), filter kategori | CS Agent, Customer | FastAPI, Pydantic | 1 | 5 | Critical | CRUD tiket berfungsi dengan response DTO tervalidasi
3.0 | Real-time Hub | WebSocket Infrastructure | Jalur komunikasi real-time 3-arah: Live Chat Widget <-> Web Dashboard <-> Mobile Flutter | Customer, CS | FastAPI WebSockets | 3 | 16 | Critical | Pesan tersinkronisasi instan <100ms
3.1 | Real-time Hub | Connection Manager & Rooms | Manajemen pool koneksi aktif, perutean broadcast pesan berdasarkan ticket_id session | Backend Eng | Python asyncio | 1 | 6 | Critical | Multi-client join room tanpa memory leak
3.2 | Real-time Hub | Always-Connected & Heartbeat | Mekanisme ping-pong 15s deteksi zombie socket, reconnect otomatis | Backend & Frontend | WebSocket Protocol | 1 | 5 | Critical | Koneksi otomatis pulih saat jaringan putus-nyambung
3.3 | Real-time Hub | Offline Message Catch-up | Sinkronisasi pesan tertinggal dengan parameter last_received_message_id saat reconnect | Backend Eng | SQLAlchemy + WS | 1 | 5 | High | Tidak ada pesan yang hilang saat client offline
4.0 | AI Bot Engine | Auto-Reply & Handoff Triage | Penanganan otomatis keluhan awal pelanggan dan eskalasi mulus ke CS manusia | Customer, AI Bot | Python, NLP / LLM API | 2.5 | 13 | High | Bot menjawab akurat dan eskalasi otomatis
4.1 | AI Bot Engine | Knowledge Base Matching | Pencocokan pertanyaan keluhan dengan FAQ Knowledge Base menggunakan similarity scoring | AI Bot | Python, TF-IDF / Gemini | 1 | 5 | High | Rekomendasi jawaban bot relevan (score >= 0.75)
4.2 | AI Bot Engine | Confidence Triage & Fallback | Deteksi jawaban tidak meyakinkan atau sentimen komplain untuk memicu eskalasi | AI Bot | State Machine Logic | 0.5 | 3 | High | Status tiket berganti WAITING_AGENT secara otomatis
4.3 | AI Bot Engine | Human Handoff Workflow | Broadcast event ticket_escalated ke Web/Mobile CS dan nonaktifkan bot saat di-claim | CS Agent, Bot | WebSocket Hub | 1 | 5 | Critical | Transisi dari bot ke CS mulus tanpa duplikasi chat
5.0 | Live Chat Widget | Embeddable Client Script | Widget chat melayang di kanan bawah website (ala Intercom) dengan Vanilla JS murni | Customer | Vanilla JS, Scoped CSS | 2.5 | 12 | Critical | Widget tampil responsif, bundle < 40 KB
5.1 | Live Chat Widget | Floating Launcher & Modal | Tombol trigger mengambang (FAB) dan popup window chat responsif tanpa merusak CSS host | Frontend Eng | HTML5, Scoped CSS | 1 | 4 | Critical | UI responsif di mobile & desktop, bebas conflict
5.2 | Live Chat Widget | WebSocket Client & UI Feed | Koneksi WebSocket client, auto-reconnect, pengiriman pesan, bubbles chat, typing indicator | Frontend Eng | Native WebSocket API | 1 | 5 | Critical | Pesan masuk real-time, status terkirim jelas
5.3 | Live Chat Widget | Interactive Action Buttons | Tombol eskalasi 'Hubungi CS Manusia', feedback rating kepuasan setelah masalah selesai | Frontend Eng | Vanilla JS Events | 0.5 | 3 | High | User dapat memicu eskalasi langsung lewat klik
6.0 | Web Dashboard | CS Workspace & Admin Panel | Aplikasi web internal untuk agen CS melayani chat dan admin memantau metrik performa | CS Agent, Admin | HTML5, Tailwind CSS, JS | 3 | 14 | Critical | Dashboard rapi, realtime feed, clean UI
6.1 | Web Dashboard | Clean Responsive UI | Desain modern, kontras WCAG AA, bebas indikator klise | UI/UX & Frontend | Tailwind CSS | 1 | 4 | High | Tampilan modern, profesional
6.2 | Web Dashboard | Real-time Ticket Kanban | Board tiket aktif dengan badge status (BOT, WAITING, ACTIVE, RESOLVED), claim button | Frontend Eng | Modular JS, WS | 1 | 5 | Critical | Tiket baru muncul seketika tanpa refresh browser
6.3 | Web Dashboard | Interactive 1-on-1 Chat Room | Panel percakapan langsung dengan customer, informasi identitas user, ganti status tiket | Frontend Eng | WebSocket Client | 1 | 5 | Critical | CS dapat membalas chat real-time dan resolve tiket
7.0 | Mobile App (CS) | Flutter Android Client | Aplikasi mobile resmi agen CS untuk melayani tiket kendala di mana saja | CS Agent | Flutter (Dart) | 3 | 12 | Critical | Aplikasi Flutter jalan lancar, siap build APK
7.1 | Mobile App (CS) | Architecture & State Setup | Scaffolding project Flutter, routing, state management untuk list tiket dan chat room | Mobile Eng | Flutter, Provider | 1 | 4 | Critical | Clean architecture, reactive state management
7.2 | Mobile App (CS) | Real-time WebSocket Client | Implementasi client WebSocket di Flutter dengan background awareness & auto-reconnect | Mobile Eng | web_socket_channel | 1 | 4 | Critical | Pesan sync real-time antara Mobile dan Web
7.3 | Mobile App (CS) | In-App Notifications & Resolution | Pemberitahuan tiket eskalasi baru dengan banner alert dan unread badge counter | Mobile Eng | Flutter Widgets | 1 | 4 | High | Badge notifikasi dan alert tiket baru aktif
8.0 | QA & Release | Verification & Delivery | Pengujian menyeluruh, audit keamanan kode, dan otomasi build APK via GitHub Actions | QA, DevOps | Pytest, GitHub Actions | 2 | 10 | Critical | Test lulus 100%, APK ter-compile otomatis
8.1 | QA & Release | Unit & Security Testing | Test suite pytest (API, WebSocket, AI deflection), sanitasi XSS pada input chat widget | QA Eng | Pytest, TestClient | 1 | 4 | Critical | Zero vulnerabilities, seluruh unit test hijau
8.2 | QA & Release | GitHub Actions CI (Build APK) | Workflow CI/CD untuk otomatis compile Flutter release APK pada commit/tag repository | DevOps Eng | GitHub Actions YAML | 0.5 | 3 | Critical | APK file artifact terbuat otomatis di GitHub
8.3 | QA & Release | Documentation & Verification | Penyusunan README lengkap, panduan run lokal 1-command, verifikasi link submission | Tech Lead | Markdown, Git | 0.5 | 3 | Critical | Seluruh deliverable take-home test siap kirim
TOTAL ESTIMASI PROYEK (HARI KERJA & BOBOT) | [5 empty] | 21 | 100 | Status: Siap Eksekusi (Ready)